## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Requirement Analysis | MUST HAVE | No Dependency | All team members | 3- Completed
S1 | S1 | US-002 | Finalize Technology Stack (React Vite Supabase, APIs) | MUST HAVE | Research & Tech Evaluation | All team members | 3- Completed
S1 | S1 | US-003 | System Architecture Design | MUST HAVE | Project Architecture Diagram | Arpita Vishwakarma, Anu Rawal | 3- Completed
S2 | S1 | US-004 | GitHub Repository & Project Structure Setup | MUST HAVE | GitHub Repository Setup | All team members | 3- Completed
S2 | S1 | US-005 | Authentication Implementation | MUST HAVE | Backend Setup | Mamatha Taneti, Shireen Naaz, C. Sai Sushmitha | 3- Completed
S2 | S2 | US-006 | Supabase Database Configuration | MUST HAVE | Database Setup | Anu Rawal, Aditi Durpade, K. Hemanth Kumar Reddy | 3- Completed
S3 | S2 | US-007 | AbuseIPDB API Integration | MUST HAVE | AbuseIPDB API Key | K. Hemanth Kumar Reddy, Amritanshu Mishra, Mamatha Taneti | 3- Completed
S3 | S2 | US-008 | AlienVault OTX Integration | MUST HAVE | AlienVault OTX API Key | Sreedatta Vajinapally, Mamatha Taneti , Arpita Vishwakarma | 3- Completed
S4 | S2 | US-009 | Threat Simulation Engine Development | MUST HAVE | Backend Logic | Shireen Naaz, Amritanshu Mishra, Aditi Durpade | 3- Completed
S4 | S2 | US-010 | Supabase Realtime Broadcasting | MUST HAVE | Supabase Setup | Anu Rawal, Mamatha Taneti, Sreedatta Vajinapally | 3- Completed
S5 | S3 | US-011 | Global Threat Map Implementation | MUST HAVE | Geo Mapping API | Mamatha Taneti, Amritanshu Mishra, K. Hemanth Kumar Reddy | 3- Completed
S5 | S3 | US-012 | Dashboard Visualizations Development | MUST HAVE | Chart Libraries | C. Sai Sushmitha, Arpita Vishwakarma, Sreedatta Vajinapally | 3- Completed
S6 | S3 | US-013 | MITRE ATT&CK Mapping Integration | MUST HAVE | MITRE Framework Reference | K. Hemanth Kumar Reddy, Shireen Naaz, C. Sai Sushmitha | 3- Completed
S6 | S3 | US-014 | Nmap Scan Module Development | MUST HAVE | Nmap Installation | Anu Rawal, C. Sai Sushmitha, Sreedatta Vajinapally | 3- Completed
S6 | S4 | US-015 | IP Reputation Module | MUST HAVE | Threat Intelligence APIs | Amritanshu Mishra, Aditi Durpade, , Sreedatta Vajinapally | 3- Completed
S7 | S4 | US-016 | QR / URL Scanner Implementation | MUST HAVE | URL Analysis Logic | Shireen Naaz, C. Sai Sushmitha, Amritanshu Mishra | 3- Completed
S7 | S4 | US-017 | AI Assistant Integration | MUST HAVE | Gemini / OpenRouter API Key | Aditi Durpade, Arpita Vishwakarma, K. Hemanth Kumar Reddy | 3- Completed
S7 | S4 | US-018 | Data Sources Page Implementation | MUST HAVE | Database APIs | Amritanshu Mishra, Sreedatta Vajinapally, Anu Rawal | 3- Completed
S8 | S4 | US-019 | System Health Monitoring | MUST HAVE | Supabase Queries | K. Hemanth Kumar Reddy, Anu Rawal, Shireen Naaz | 3- Completed
S8 | S5 | US-020 | Role-Based Dashboard Implementation | MUST HAVE | Authentication System | C. Sai Sushmitha, Amritanshu Mishra, Mamatha Taneti | 3- Completed
S8 | S5 | US-021 | Data Optimization & Performance Tuning | MUST HAVE | Backend Optimization | Shireen Naaz, Aditi Durpade, Sreedatta Vajinapally | 3- Completed
S9 | S5 | US-022 | System Testing | MUST HAVE | Integrated Module Testing | Arpita Vishwakarma, K. Hemanth Kumar Reddy, Aditi Durpade | 3- Completed
S9 | S5 | US-023 | Bug Fixing | MUST HAVE | Complete System | Aditi Durpade, Anu Rawal, Mamatha Taneti | 3- Completed
S9 | S5 | US-024 | Agile Documentation Preparation | MUST HAVE | Project Documentation | Arpita Vishwakarma, Shireen Naaz, C. Sai Sushmitha | 3- Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Members | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-001 | 1 | Project Requirement Analysis | 2026-02-03 | 2026-02-05 | All team members | Planning | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 2 | Finalize Technology Stack (React Vite Supabase, APIs) | 2026-02-05 | 2026-02-06 | All team members | Planning | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 3 | System Architecture Design | 2026-02-09 | 2026-02-12 | Arpita Vishwakarma, Anu Rawal | Planning | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 4 | GitHub Repository & Project Structure Setup | 2026-02-12 | 2026-02-16 | All team members | Setup | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 5 | Authentication Implementation | 2026-02-17 | 2026-02-18 | Mamatha Taneti, Shireen Naaz, C. Sai Sushmitha | Setup | 3- Completed | 12 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 6 | Supabase Database Configuration | 2026-02-18 | 2026-02-20 | Anu Rawal, Aditi Durpade, K. Hemanth Kumar Reddy | Setup | 3- Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 7 | AbuseIPDB API Integration | 2026-02-23 | 2026-02-25 | K. Hemanth Kumar Reddy, Amritanshu Mishra, Mamatha Taneti | Setup | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | 8 | AlienVault OTX Integration | 2026-02-25 | 2026-02-26 | Sreedatta Vajinapally, Mamatha Taneti , Arpita Vishwakarma | Setup | 3- Completed | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | 9 | Threat Simulation Engine Development | 2026-02-26 | 2026-02-27 | Shireen Naaz, Amritanshu Mishra, Aditi Durpade | Coding | 3- Completed | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | 10 | Supabase Realtime Broadcasting | 2026-03-02 | 2026-03-05 | Anu Rawal, Mamatha Taneti, Sreedatta Vajinapally | Coding | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | 11 | Global Threat Map Implementation | 2026-03-05 | 2026-03-06 | Mamatha Taneti, Amritanshu Mishra, K. Hemanth Kumar Reddy | Coding | 3- Completed | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | 12 | Dashboard Visualizations Development | 2026-03-07 | 2026-03-10 | C. Sai Sushmitha, Arpita Vishwakarma, Sreedatta Vajinapally | Coding | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | 13 | MITRE ATT&CK Mapping Integration | 2026-03-11 | 2026-03-13 | K. Hemanth Kumar Reddy, Shireen Naaz, C. Sai Sushmitha | Coding | 3- Completed | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | 14 | Nmap Scan Module Development | 2026-03-16 | 2026-03-17 | Anu Rawal, C. Sai Sushmitha, Sreedatta Vajinapally | Coding | 3- Completed | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | 15 | IP Reputation Module | 2026-03-17 | 2026-03-19 | Amritanshu Mishra, Aditi Durpade, , Sreedatta Vajinapally | Coding | 3- Completed | 12 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | 16 | QR / URL Scanner Implementation | 2026-03-19 | 2026-03-20 | Shireen Naaz, C. Sai Sushmitha, Amritanshu Mishra | Coding | 3- Completed | 10 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-017 | 17 | AI Assistant Integration | 2026-03-23 | 2026-03-24 | Aditi Durpade, Arpita Vishwakarma, K. Hemanth Kumar Reddy | Coding | 3- Completed | 10 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-018 | 18 | Data Sources Page Implementation | 2026-03-24 | 2026-03-25 | Amritanshu Mishra, Sreedatta Vajinapally, Anu Rawal | Coding | 3- Completed | 10 | 4 | 2 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-019 | 19 | System Health Monitoring | 2026-03-25 | 2026-03-26 | K. Hemanth Kumar Reddy, Anu Rawal, Shireen Naaz | Coding | 3- Completed | 10 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-020 | 20 | Role-Based Dashboard Implementation | 2026-03-26 | 2026-03-27 | C. Sai Sushmitha, Amritanshu Mishra, Mamatha Taneti | Documentation | 3- Completed | 12 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-021 | 21 | Data Optimization & Performance Tuning | 2026-03-25 | 2026-03-27 | Shireen Naaz, Aditi Durpade, Sreedatta Vajinapally | Documentation | 3- Completed | 12 | 4 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-022 | 22 | System Testing | 2026-03-26 | 2026-03-27 | Arpita Vishwakarma, K. Hemanth Kumar Reddy, Aditi Durpade | Documentation | 3- Completed | 10 | 4 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-023 | 23 | Bug Fixing | 2026-03-24 | 2026-03-26 | Aditi Durpade, Anu Rawal, Mamatha Taneti | Documentation | 3- Completed | 10 | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-024 | 24 | Agile Documentation Preparation | 2026-03-23 | 2026-03-27 | Arpita Vishwakarma, Shireen Naaz, C. Sai Sushmitha | Documentation | 3- Completed | 10 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Confusion in finalizing 4-layer system architecture design | Conducted team discussion and finalized initial microservice-based structure after GitHub initialization and 3D globe integration.
Sprint 1 | Day 5 | Difficulty integrating multiple heterogeneous threat intelligence APIs (OTX / AbuseIPDB) during early phase | Developed a normalization middleware to standardize varied API responses into a unified JSON format.
Sprint 1 | Day 7 | Inconsistent API response formats across different security providers | Implemented dynamic response parsing and validation logic for uniform data handling.
Sprint 2 | Day 10 | API key exhaustion occurring multiple times and rate-limiting during high-frequency threat polling | Implemented Redis-based request scheduling and optimized API usage strategy to reduce redundant calls.
Sprint 2 | Day 12 | Demo dashboard showing unstable or partial threat data during initial frontend-backend sync. | Stabilized the data bus by moving from basic polling to Supabase Realtime broadcasting.
Sprint 2 | Day 14 | Structural inefficiencies identified during mentor review | Refactored backend logic into the Medallion Architecture (Bronze/Silver/Gold) for optimized data flow.
Sprint 2 | Day 15 | AbuseIPDB integration failing intermittently due to timeout errors. | Restructured request handling with asynchronous background tasks and retry logic until stable.
Sprint 3 | Day 18 | Dashboard performance extremely slow during aggregation | Replaced heavy runtime calculations with database views and reduced high-cost aggregation operations.
Sprint 3 | Day 20 | Over-dependency on flat-file (CSV/Excel) intermediate storage causing data lag. | Removed intermediate file layers and shifted to a direct database-driven architecture via Supabase.
Sprint 3 | Day 22 | AlienVault OTX API architecture creating complexity and delays | Simplified system design by removing OTX-heavy architecture, restructuring data flow and streamlining the Silver Tier mapping process.
Sprint 4 | Day 25 | Scalability limitations discovered when rendering 1,000+ markers on the 3D Globe. | Rebuilt the globe component using GLSL shaders and modular React-Fiber structures for better FPS.
Sprint 4 | Day 27 | Final system optimization of redundant code and "dead logic" bloating the final production build before submission | Performed tree-shaking, cleaned unused dependencies, and optimized the final Vite build before submission.
Sprint 4 | Day 29 | Documentation inconsistencies regarding MITRE ATT&CK mapping logic. | Standardized the technical definitions and finalized the Agile Sprint Report with mapped TTPs.
Sprint 5 | Day 33 | Version compatibility conflicts between LangChain and Gemini LLM dependencies. | Locked specific NPM package versions and created a consistent requirements.txt / package.json config.
Sprint 5 | Day 35 | Real-time updates failing to broadcast correctly during WebSocket stress testing. | Debugged event listeners in the WebSocket Controller and optimized the broadcasting frequency.
Sprint 5 | Day 37 | Database indexing missing in the initial schema, leading to slow IP lookups. | Added indexing on frequently queried fields like ip_address and severity_level to improve performance.
Sprint 5 | Day 39 | Improper or silent error handling during critical API connection failures | Implemented a centralized Error Boundary and fallback UI mechanisms for a resilient user experience.
Sprint 5 | Day 40 | Team coordination delays during final system restructuring phase | Conducted focused Daily Stand-ups and redistributed backend tasks to clear the development bottleneck.

## Retrospection
Sprint # | Sprint | Sprint start date | Sprint end date | Team members Name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-02 | 2026-02-16 | All team members | Clearly defining requirements, architecture and DB schema before coding | Starting development without finalizing FastAPI / Superbase environment setup | Daily stand-ups and GitHub Projects for task tracking. | Finalized technical SRS and initialized the modular backend-frontend project structure.
2 | Sprint 2 | 2026-02-17 | 2026-03-02 | All team members | Implement structured backend modules with validation and proper schema mapping | Making external API calls to OTX/AbuseIPDB without rate-limit handling. | Cross-team collaboration on API normalization and error handling. | Developed a middleware for request scheduling and standardized JSON responses for all feeds.
3 | Sprint 3 | 2026-03-03 | 2026-03-16 | All team members | Improving 3D globe performance, real-time websocket broadcasting and dashboard responsiveness | Using static mock data for frontend validation; move to live Supabase data. | Cross-team automated testing of Medallion Pipeline (Bronze ---> Silver ---> Gold). testing during feature integration | Optimized GLSL shaders and moved to a fully database-driven real-time update system.
4 | Sprint 4 | 2026-03-17 | 2026-03-27 | All team members | Strengthen superbase RLS policies, AI forensics validation and threat validation mechanisms | Ignoring edge cases in Nmap scan validation and URL analysis. | Peer code reviews before merging security and SOAR automation logic. | Implemented Row-Level Security, fine-tuned the Gemini AI Agent prompts, and finalized the SOAR engine playbooks.